## Summary
Daily Report - Day 1
Date | 2025-11-23
Build | 1.0
Team List: |  | Name
| - Test Lead | Lê Hoàng Đạt
| - Tester 1 | Lê Thanh Phong
| - Tester 2 | Nguyễn Thị Kim Thoa
Achievements: | # | Name |  |  |  | % Completed | Notes
| 1 | Create a State Transition Table to verify the behavior of the shopping cart, focusing on the following actions: adding, removing, cancel removing, undo removing, increasing, and decreasing items. |  |  |  | 100%
| 2 | Create a Decision Table to test the order placement logic based on the conditions |  |  |  | 100%
| 3 | Create a Checklist to test the coupon functionality (add/remove), and verify whether the system applies the correct discount. |  |  |  | 100%
Test Results: |  | Matrix | TC List | Total | %
| Passed | 43 | 0 | 43 | 25%
| Failed | 6 | 0 | 6 | 25%
| Blocked | 0 | 0 | 0 | 25%
| Skip | 0 | 0 | 0 | 25%
| Total: | 49 | 0 | 49 | 100%
Bug Status |  | # | %
| New | 0 | 0%
| Assigned | 0 | 0%
| In Progress | 0 | 0%
| Fixed | 0 | 0%
| In Verification | 0 | 0%
| Re-opened | 0 | 0%
| Closed | 0 | 0%
| Rejected | 0 | 0%
| Total: | 0 | 0%
Daily Report - Day 2
Date | 24-Nov-2025
Build | 1.0
Team 1 |  | Name
| - Test Lead | Nguyễn Thị Kim Thoa
| - Tester 1 | Lê Hoàng Đạt
| - Tester 2 | Lê Thanh Phong
Achievements: | # | Name |  |  |  | % Completed | Notes
| 1 | Design Test Cases and submit test results for Build 1 on Windows platform. |  |  |  | 50%
| 2 | Perform Ad-hoc testing and submit bug reports for Build 1 on Windows and Mobile |  |  |  | 50%
Test Results: |  | Matrix | TC List | Total | %
| Passed | 43 | 39 | 82 | 25%
| Failed | 6 | 19 | 25 | 25%
| Blocked | 0 | 0 | 0 | 25%
| Skip | 0 | 0 | 0 | 25%
| Total: | 49 | 58 | 107 | 100%
Bug Status |  | # | %
| New | 11
| Assigned | 0
| In Progress | 0
| Fixed | 0
| In Verification | 0
| Re-opened | 0
| Closed | 0
| Rejected | 0
| Total: | 11
Daily Report - Day 3
Date | 16-Jan-25
Build | 2.0
Team 1 |  | Name
- Test Lead
- Tester 1
- Tester 2
- Tester 3
- Tester 4
- Tester 5
- Tester 6
- Tester 7
Achievements: | # | Name |  |  |  | % Completed | Notes
1
2
3
Test Results: |  | Matrix | TC List | Total | %
| Passed | 1 | 0 | 1 | 25%
| Failed | 1 | 0 | 1 | 25%
| Blocked | 1 | 0 | 1 | 25%
| Skip | 1 | 0 | 1 | 25%
| Total: | 4 | 0 | 4 | 100%
Bug Status |  | # | %
| New | 1 | 13%
| Assigned | 1 | 13%
| In Progress | 1 | 13%
| Fixed | 1 | 13%
| In Verification | 1 | 13%
| Re-opened | 1 | 13%
| Closed | 1 | 13%
| Rejected | 1 | 13%
| Total: | 8 | 100%
Daily Report - Day 4
Date | 18-Jan-25
Build | 3.0
Team 1 |  | Name
- Test Lead
- Tester 1
- Tester 2
- Tester 3
- Tester 4
- Tester 5
- Tester 6
- Tester 7
Achievements: | # | Name |  |  |  | % Completed | Notes
1
2
3
Test Results: |  | Matrix | TC List | Total | %
| Passed | 1 | 0 | 1 | 25%
| Failed | 1 | 0 | 1 | 25%
| Blocked | 1 | 0 | 1 | 25%
| Skip | 1 | 0 | 1 | 25%
| Total: | 4 | 0 | 4 | 100%
Bug Status |  | # | %
| New | 1 | 13%
| Assigned | 1 | 13%
| In Progress | 1 | 13%
| Fixed | 1 | 13%
| In Verification | 1 | 13%
| Re-opened | 1 | 13%
| Closed | 1 | 13%
| Rejected | 1 | 13%
| Total: | 8 | 100%
Team Contribution
Name | Matrix | # of TCs Created | # of TCs Executed | # of Reviewed TCs | Urgent | High | Medium | Low | # of Reviewed Bugs | # of Regressed 1 | # of Regressed 2 | Scoring
Hoa | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Huy | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Matrix
Matrix
State Transition Table: | S0 | Empty
| S1 | Quantity equal to 1
| S2 | Quantity greater than 1
| S3 | Pending Remove
| S4 | Removed
| S5 | Quantity equal to 2
| TC# | Start State | Event | End State | Test Result | Note | Create by | Review by | Build 1.0 |  | Build 2.0 |  | Build 3.0
[9 empty] | Test Result | Executed by | Test Result | Executed by | Test Result | Executed by
| 1 | S0 | Add item | S1 | Pass | _ User can add item to cart _ Quantity = S1 | Phong | Đạt | Pass | Phong
| 2 | S0 | Add item | S2 | Pass | _ User can add item to cart _ Quantity = S2 | Phong | Đạt | Pass | Phong
| 3 | S1 | Add item | S2 | Pass | _ User can add item to cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 4 | S2 | Add item | S2 | Pass | _ User can add item to cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 5 | S4 | Add item | S1 | Pass | _ User can add item to cart _ Quantity = S1 | Phong | Đạt | Pass | Phong
| 6 | S4 | Add item | S2 | Pass | _ User can add item to cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 7 | S3 | Add item | S1 | Pass | _ User can add item to cart _ Quantity = S1 | Phong | Đạt | Pass | Phong
| 8 | S3 | Add item | S2 | Pass | _ User can add item to cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 9 | S1 | Remove item | S0 | Pass | _ User can remove item from cart _ Not in cart | Phong | Đạt | Pass | Phong
| 10 | S2 | Remove item | S0 | Pass | _ User can remove item from cart _ Not in cart | Phong | Đạt | Pass | Phong
| 11 | S1 | Cancel removing item | S1 | Pass | _ User can cancel removing item from cart _ Quantity = S1 quantity | Phong | Đạt | Pass | Phong
| 12 | S2 | Cancel removing item | S2 | Pass | _ User can cancel removing item from cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 13 | S0 | Undo removing item | S1 | Pass | _ User can undo removing item from cart _ Quantity = S1 quantity | Phong | Đạt | Pass | Phong
| 14 | S0 | Undo removing item | S2 | Pass | _ User can undo removing item from cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 15 | S1 | Undo removing item | S2 | Pass | _ User can undo removing item from cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 16 | S2 | Undo removing item | S2 | Pass | _ User can undo removing item from cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
|  | S3 | Undo removing item | S1 | Pass | _ User can undo removing item from cart _ Quantity = S1 quantity | Phong | Đạt | Pass | Phong
|  | S3 | Undo removing item | S2 | Pass | _ User can undo removing item from cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 17 | S1 | Increase item | S2 | Pass | _ User can increase item from cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 18 | S2 | Increase item | S2 | Pass | _ User can increase item from cart _ Quantity = S2 quantity | Phong | Đạt | Pass | Phong
| 19 | S5 | Decrease item | S1 | Pass | _ User can decrease item from cart _ Quantity = S1 quantity | Phong | Đạt | Pass | Phong
| 20 | S6 | Decrease item | S6 | Pass | _ User can decrease item from cart _ Quantity = S6 quantity _ Quantity different 0 | Phong | Đạt | Pass | Phong
| 21 | S6 | Decrease item | S1 | Pass | _ User can decrease item from cart _ Quantity = S1 quantity | Phong | Đạt | Pass | Phong
Decision Table: | # | C1:Cart >=1 product | C2:Logged in user | C3:Payment information | Expected Result | Created by | Reviewed by | Build 1.0 |  | Build 2.0 |  | Build 3.0
[8 empty] | Test Result | Executed by | Test Result | Executed by | Test Result | Executed by
| 1 | FALSE | FALSE | FALSE | Payment not allowed | Thoa | Đạt | Fail | Thoa
| 2 | FALSE | FALSE | TRUE | Payment not allowed | Thoa | Đạt | Fail | Thoa
| 3 | FALSE | TRUE | FALSE | Payment not allowed | Thoa | Đạt | Fail | Thoa
| 4 | FALSE | TRUE | TRUE | Payment not allowed | Thoa | Đạt | Fail | Thoa
| 5 | TRUE | TRUE | TRUE | Payment is allowed | Thoa | Đạt | Pass | Thoa
| 6 | TRUE | TRUE | FALSE | Payment is allowed | Thoa | Đạt | Pass | Thoa
| 7 | TRUE | FALSE | TRUE | Payment is allowed | Thoa | Đạt | Pass | Thoa
| 8 | TRUE | FALSE | FALSE | Payment not allowed | Thoa | Đạt | Fail | Thoa
Check List: | # | Description | Expected Result | Test Result | Notes | Created by | Reviewed by | Build 1.0 |  | Build 2.0 |  | Build 3.0
[8 empty] | Test Result | Executed by | Test Result | Executed by | Test Result | Executed by
| 1 | Add actp10 coupon will discount product 10% after applying code | product price has been reduced by 10% | Pass |  | Đạt | Đạt | Pass | Đạt
| 2 | Remove actp10 coupon will lose 10% product discount | product prices will not be reduced by 10% | Pass |  | Đạt | Đạt | Pass | Đạt
| 3 | Add actp20 coupon will discount product 20% after applying code | product price has been reduced by 20% | Pass |  | Đạt | Đạt | Pass | Đạt
| 4 | Remove actp20 coupon will lose 20% product discount | product prices will not be reduced by 20% | Pass |  | Đạt | Đạt | Pass | Đạt
| 5 | Add actp30 coupon will discount product 30% after applying code | product price has been reduced by 30% | Pass |  | Đạt | Đạt | Pass | Đạt
| 6 | Remove actp30 coupon will lose 30% product discount | product prices will not be reduced by 30% | Pass |  | Đạt | Đạt | Pass | Đạt
| 7 | Add actp40 coupon will discount product 40% after applying code | product price has been reduced by 40% | Pass |  | Đạt | Đạt | Pass | Đạt
| 8 | Remove actp40 coupon will lose 40% product discount | product prices will not be reduced by 40% | Pass |  | Đạt | Đạt | Pass | Đạt
| 9 | Add actp50 coupon will discount product 50% after applying code | product price has been reduced by 50% | Pass |  | Đạt | Đạt | Pass | Đạt
| 10 | Remove actp50 coupon will lose 50% product discount | product prices will not be reduced by 50% | Pass |  | Đạt | Đạt | Pass | Đạt
| 11 | Add actp100 coupon will discount product 100% after applying code | product price has been reduced by 100% | Fail |  | Đạt | Đạt | Fail | Đạt
| 12 | Remove actp100 coupon will lose 100% product discount | product prices will not be reduced by 100% | Pass |  | Đạt | Đạt | Pass | Đạt
| 13 | Add actp10usd coupon will discount product 10usd after applying code | product price has been reduced by 10usd | Pass |  | Đạt | Đạt | Pass | Đạt
| 14 | Remove actp10usd coupon will lose 10usd product discount | product prices will not be reduced by 10usd | Pass |  | Đạt | Đạt | Pass | Đạt
| 15 | Add actp20usd coupon will discount product 20usd after applying code | product price has been reduced by 20usd | Pass |  | Đạt | Đạt | Pass | Đạt
| 16 | Remove actp20usd coupon will lose 20usd product discount | product prices will not be reduced by 20usd | Pass |  | Đạt | Đạt | Pass | Đạt
| 17 | Add actp30usd coupon will discount product 30usd after applying code | product price has been reduced by 30usd | Pass |  | Đạt | Đạt | Pass | Đạt
| 18 | Remove actp30usd coupon will lose 30usd product discount | product prices will not be reduced by 30usd | Pass |  | Đạt | Đạt | Pass | Đạt

## Test Case List
Test Case List
TC ID | TC Description | Pre-Condition | Steps | Expected Result | Status | Smoke Test | Created Date | Created by | Reviewed by | Build 1.0 |  | Build 2.0 |  | Build 3.0 |  | Bug ID | Notes
[10 empty] | Test Result | Executed by | Test Result | Executed by | Test Result | Executed by
Register
RGT-01 | Verify that user register successfully with correct email and password. |  | 1.Lauch website agest 2.Input correct email 3.Input correct password 4.Click button "Register" | Register successfully. Website open page "MY ACCOUNT". |  |  | 24-Nov-2025 | Đạt |  | Pass
RGT-02 | Verify that user register fail with incorrect email. |  | 1.Lauch website agest 2.Input incorrect email(qwerty@gmail) 3.Input password 4.Click button "Register" | Display show "Error: Please provide a valid email address." |  |  | 24-Nov-2025 | Đạt |  | Pass
RGT-03 | Verify that user register fail with correct email but incoorect password. |  | 1.Lauch website agest 2.Input correct email 3.Input incorrect password(123456789) 4.Click button "Register" | Display show "Very weak - Please enter a stronger password." |  |  | 24-Nov-2025 | Đạt |  | Pass
RGT-04 | Verify that the password should be at least twelve characters long. To make it stronger, use upper and lower case letters, numbers, and symbols like ! " ? $ % ^ & ) |  | 1.Open page "MY ACCOUNT" for Agest 2.User select password textbox 3.User input password 4.User input 12 character, contain 1 special character, upper and lower case (!123Qw789er@) | Display field password show:"Strong" |  |  | 24-Nov-2025 | Đạt |  | Pass
RGT-05 | Verify that the password less twelve characters long. To make it stronger, use upper and lower case letters, numbers, and symbols like ! " ? $ % ^ & ) |  | 1.Open page "MY ACCOUNT" for Agest 2.User select password textbox 3.User input password 4.User input less 12 character, contain 1 special character, upper and lower case (14Zxc!7369) | Display field password show:"Weak - Please enter a stronger password." |  |  | 24-Nov-2025 | Đạt |  | Fail | [5 empty] | Bug 12
RGT-06 | Verify that user register fail with empty email. |  | 1.Lauch website agest 2.Field email not input 3.Input password 4.Click button "Register" | Display field email show: "Please fill out this field" |  |  | 24-Nov-2025 | Đạt |  | Pass
RGT-07 | Verify that user register fail with empty password. |  | 1.Lauch website agest 2.Input email 3.Field password not input 4.Click button "Register" | Display field password show: "Please fill out this field" |  |  | 24-Nov-2025 | Đạt |  | Pass
RGT-08 | Verify that user register fail with empty email and password. |  | 1.Lauch website agest 2.Field email not input 3.Field password not input 4.Click button "Register" | Display field email show: "Please fill out this field" |  |  | 24-Nov-2025 | Đạt |  | Pass
RGT-09 | Verify that there is a limit to the length that can be entered in the pass field. |  | 1.Lauch website agest 2.Enter a long string into the pass field | There is a posted limit on the number of people allowed in the parking area. |  |  | 24-Nov-2025 | Đạt |  | Fail | [5 empty] | Bug 13
Login
LGI_01 | Verify that user can login successfully with correct username/email and password. | Has account Agest | 1.Lauch website agest 2.Input correct email 3.Input correct password 4.Click button "Log In" | Login successfully. Website open page "MY ACCOUNT". |  |  | 24-Nov-2025 | Đạt |  | Pass
LGI_02 | Verify that user can't login successfully with incorrect username/email and correct password. |  | 1.Lauch website agest 2.Input incorrect email 3.Input correct password 4.Click button "Log In" | Display show "The username is not registered on this site. If you are unsure of your username, try your email address instead." |  |  | 24-Nov-2025 | Đạt |  | Pass
LGI_03 | Verify that user can't login successfully with correct username/email and incorrect password. |  | 1.Lauch website agest 2.Input correct email 3.Input incorrect password 4.Click button ""Log In" | Display show "Error: The password you entered for the username is incorrect. Lost your password?" |  |  | 24-Nov-2025 | Đạt |  | Pass
LGI_04 | Verify that user can't login successfully with empty username/email |  | 1.Lauch website agest 2.Field email not input 3.Input password 4.Click button "Log In" | Display show username field "Please fill out this field" |  |  | 24-Nov-2025 | Đạt |  | Fail | [5 empty] | Bug 14
LGI_05 | Verify that user can't login successfully with empty password |  | 1.Lauch website agest 2.Input email 3.Field password not input 4.Click button "Log In" | Display show password field "Please fill out this field" |  |  | 24-Nov-2025 | Đạt |  | Pass
LGI_06 | Verify that user can't login successfully with empty email/username and password |  | 1.Lauch website agest 2.Field email not input 3.Field password not input 4.Click button "Log In" | Display show email/username and password field "Please fill out this field" |  |  | 24-Nov-2025 | Đạt |  | Fail | [5 empty] | Bug 15
Product
PD_01 | Verify that cart is added successfully when customer adds product. | User on the shop page. | 1. Launch the AGEST website 2. Go to "Shop" 3. Select product 4. Click "Add to Cart" | _User has successfully added the product. _The "Bold Statement Graphic Tee" page will appear. _The text "Bold Statement Graphic Tee" has been added to your cart. View cart. | Add |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
PD_02 | Verify that reviews are added when customers want to reviews products. | User on the shop page. | 1. Launch the AGEST website 2. Go to "Shop" 3. Select product 4. Click "Reviews" 5.Select stars rating and enter reviews | _Reviews added. _The "Reviews" page will appear. _Customer reviews added. | Reviews |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
PD_03 | Verify that reviews display the number of reviews when a customer has rated a product. | User on the shop page. | 1. Launch the AGEST website 2. Go to "Shop" 3. Select product 4. Click "Reviews" | The number of reviews is not updated. | Reviews |  | 24-Nov-2025 | Thoa |  | Fail | Thoa |  |  |  |  | Bug 1
Shopping Cart
SC_01 | Verify that the product is deleted successfully when the customer deletes the product. | User on the shopping cart page. | 1. Go to AGEST website 2. Go to "Cart" 3. Click "X" to delete product. | _The user has successfully deleted the product. _The "Shoping Cart" page will appear. _“Bold Statement Graphic Tee” removed. Undo? | Delete |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
SC_02 | Verify that the product quantity is updated successfully when the customer updates the product. | User on the shopping cart page. | 1. Go to AGEST website 2. Go to "Cart" 3. Click textbox update quantity 4.Click "Update cart" | _User did not update the product. _The "Cart" page will appear. _Sorry, we are currently experiencing technical difficulties with our cart system. Please try again later. | Update |  | 24-Nov-2025 | Thoa |  | Fail | Thoa |  |  |  |  | Bug 2
SC_03 | Verify that the product is discounted when the customer enters the coupon code. | User on the shopping cart page. | 1. Go to AGEST website 2. Go to "Cart" 3. Enter cuopon code 4.Click "Apply coupont" | _The product is on sale. _The "Cart" page will appear. _Coupon code applied successfully. | Coupon |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
SC_04 | Verify that coupons do not change when customers enter duplicate coupons. | User on the shopping cart page. | 1. Go to AGEST website 2. Go to "Cart" 3. Enter cuopon code 4.Click "Apply coupont" | _Discounted products cannot be discounted again if the same discount code is used. _The "Cart" page to the right of the apply coupon button will appear. _Coupon code already applied. | Coupon |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
SC_05 | Verify that the coupon is changed when the customer enters a different coupon. | User on the shopping cart page. | 1. Go to AGEST website 2. Go to "Cart" 3. Enter cuopon code 4.Click "Apply coupont" | _The product is on sale. _The "Cart" page will appear. _Coupon code applied successfully. | Coupon |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
SC_05 | Verify that the coupon has been removed when the customer removes the coupon. | User on the shopping cart page. | 1. Go to AGEST website 2. Go to "Cart" 3. Enter cuopon code 4.Click "Apply coupont" 5.Click"[Removed]" | _Coupon code has been removed. _The "Cart" page will appear. _Coupon has been removed. | Coupon |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
Checkout
CO_01 | Verify that customer information is always blank when the customer is not logged in. | User on the checkout page. | 1. Go to AGEST website 2. Go to "Cart" 3. Click "Proceed to checkout" | _Customer information is blank. _The "Checkout" page will appear. _Returning customer? Click here to login _Have a coupon? Click here to enter your code. | Information |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
CO_02 | Verify that customer information is pre-filled when the customer is logged in. | User on the checkout page. | 1. Go to AGEST website 2. Go to "Cart" 3. Click "Proceed to checkout" | _Customer information already filled in. _The "Checkout" page will appear. _Have a coupon? Click here to enter your code. | Information |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
CO_02 | Verify that the order has been placed successfully when the customer has placed the order. | User on the checkout page. | 1. Go to AGEST website 2. Go to "Cart" 3. Click "Proceed to checkout" 4.Click "Place order" | _Order successful. _The "Checkout" page will appear. _Thank you. Your order has been received. | Order |  | 24-Nov-2025 | Thoa |  | Pass | Thoa
Search
SH-01 | Verify that the system shows search textbox when user clicks search icon (magnifying glass) on the menu bar. |  | 1. Laurch Agest website 2. Click on search icon (magnifyning glass) on the menu bar | The system displays a search text box at the top of the website. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
SH-02 | Verify that the system returns results matching the search results when the customer enters keywords into the text box. | User successfully opens search bar | 1. Laurch Agest website 2. Open search bar 3. Enter a correct keyword into the text box | The system returns results matching the search results. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
SH-03 | Verify that the system displays the correct search box placeholder text when the user opens the search bar. | User successfully opens search bar | 1. Laurch Agest website 2. Open search bar | The placeholder text of the search box is "Search for ...". |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
SH-04 | Verify that the system displays the correct color of the border when the user opens the search bar. | User successfully opens search bar | 1. Laurch Agest website 2. Open search bar | The border color of the search box is blue. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
SH-05 | Verify that the system displays an error message when the user enters special characters in the search bar (ex: @,#,$,^,...). | User successfully opens search bar | 1. Laurch Agest website 2. Open search bar 3. Enter special characters (ex: @,#,$,^,...) | _The system displays an error box to the left of the search bar. _In the error box, there is an exclamation point icon with a red border. _The user cannot continue typing. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
SH-06 | Verify that correct UI display system of search box close icon. | User successfully opens search bar | 1. Laurch Agest website 2. Open search bar | _Icon: x. _Color: black. _Location: the top right corner of the search box. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
SH-07 | Verify that the system displays the correct function of the search box close icon when the user wants to close the search box. | User successfully opens search bar | 1. Laurch Agest website 2. Open search bar 3. Click on "x" icon on the top right corner of the search box | The system will close the search box when the user clicks on the search box close icon. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
Home
HO-01 | Verify that the system displays the product detail page when the user clicks on the product image or name. | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page 3. Click on the product image or name | The system opens the detail page of the selected product. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-02 | Verify that the system displays the correct product price when the user opens the "Home" page | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page | The system displays the product price the same as the product price in the product detail page. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-03 | Verify that the system displays the correct product price UI when the user opens the "Home" page | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page | The system displays the correct product price interface. (ex: $<PRICE>) |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-04 | Verify that the system displays the correct UI of the original price before the discount when the user opens the "Home" page. | _User opens "Home" page _Products with discounts | 1. Laurch Agest website 2. Go to "Home" page | _The system displays the correct original product price interface before the discount. (ex: $<PRICE>). _Lies to the left of the price after the drop. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-05 | Verify that the system opens "Shop" page when the user clicks the "SEE ALL PRODUCTS" button on the first banner. | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page 3. Click on the first "SEE ALL PRODUCTS" button | The system opens "Shop" page. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-06 | Verify that the system opens "Shop" page when the user clicks the "VIEW COLLECTIONS" button. | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page 3. Click "VIEW COLLECTIONS" button | The system opens "Shop" page. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-07 | Verify that the system opens the "Shop" page when the user clicks on the "VIEW ALL PRODUCTS" button on top of the second banner. | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page 3. Click on the second "SEE ALL PRODUCTS" button | The system opens "Shop" page. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-08 | Verify that the mouse pointer is a hand when the user hovers over all buttons on the "home" page. | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page 3. Hover over all button | The mouse pointer is a hand. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-09 | Verify that the system displays the correct 4 columns of product groups when the user opens "Home" page. | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page | The system displays the correct 4 columns of product groups. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
HO-10 | Verify that product titles change color correctly when users hover over them. | User opens "Home" page | 1. Laurch Agest website 2. Go to "Home" page | _Product titles change color when users hover over them. _Hover State Color: blue. |  |  | 25-Nov-2025 | Phong |  | Pass | Phong
Blog
BG-01 | Verify that every shortened article on the homepage has a "Read more" link when users want to access the full content. | User opens "Blog" page | 1. Laurch Agest website 2. Go to "Blog" page | Every shortened article on the homepage has a "Read more" link. |  |  | 25-Nov-2025 | Phong |  | Fail | Phong
BG-02 | Verify that the system correctly redirects to the post detail page when users click on post images that act as links | User opens "Blog" page | 1. Laurch Agest website 2. Go to "Blog" page | The system correctly redirects to the post detail page. |  |  | 25-Nov-2025 | Phong |  | Fail | Phong
BG-03 | Verify that the system correctly redirects to the post detail page when users click on post titles that act as links | User opens "Blog" page | 1. Laurch Agest website 2. Go to "Blog" page | The system correctly redirects to the post detail page. |  |  | 25-Nov-2025 | Phong |  | Fail | Phong
My Account
MA_01 | Verify that "First name" in page "Billing address" not allows to enter numbers and special characters |  | 1.User launch website Agest 2.User Login 3.At page press "Address" 4.User press "Edit Billing address" 5. Field "Frist name" input number or special character | Display an invalid ‘First name’ field error message. |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 16
MA_02 | Verify that "Last name" in page "Billing address" not allows to enter numbers and special characters |  | 1.User launch website Agest 2.User Login 3.At page press "Address" 4.User press "Edit Billing address" 5. Field "Last name" input number or special character | Display an invalid ‘Last name’ field error message. |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 17
MA_03 | Verify that the 'phone' field on the 'Billing Address' page is in the correct format of a phone number. |  | 1.User launch website Agest 2.User Login 3.At page press "Address" 4.User press "Edit Billing address" 5. Field "Phone" input 999999999999999999 | Display an invalid ‘Phone’ field error message. |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 18
MA_04 | .Verify that display show message Save address successfully in "Billing address" page when click button "Save address" |  | 1.User launch website Agest 2.User Login 3.At page press "Address" 4.User press "Edit Billing address" 5.Input all field in "Shipping address" page 6.User press button "Save address" | Display show: "Address changed successfully." |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 19
MA_05 | Verify that "First name" in page "Shipping address" not allows to enter numbers and special characters |  | 1.User launch website Agest 2.User Login 3.At page press "Address" 4.User press "Edit Shipping address" 5. Field "Frist name" input number or special character | Display an invalid ‘First name’ field error message. |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 20
MA_06 | Verify that "Last name" in page "Shipping address" not allows to enter numbers and special characters |  | 1.User launch website Agest 2.User Login 3.At page press "Address" 4.User press "Edit Shipping address" 5. Field "Last name" input number or special character | Display an invalid ‘Last name’ field error message. |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 21
MA_07 | .Verify that display show message Save address successfully in "Shipping address" page when click button "Save address" |  | 1.User launch website Agest 2.User Login 3.At page press "Address" 4.User press "Edit Shipping address" 5.Input all field in "Shipping address" page 6.User press button "Save address" | Display show: "Address changed successfully." |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 22
MA_08 | Verify that "First name" in page "Account details" not allows to enter numbers and special characters |  | 1.User launch website Agest 2.User Login 3.At page press "Account details" 4.Field "Frist name" input number or special character | Display an invalid ‘First name’ field error message. |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 23
MA_09 | Verify that "Last name" in page "Account details" not allows to enter numbers and special characters |  | 1.User launch website Agest 2.User Login 3.At page press "Account details" 4.Field "Last name" input number or special character | Display an invalid ‘Last name’ field error message. |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 24
MA_10 | Verify that user can change new password when user wants to change password. |  | 1.User launch website Agest 2.User Login 3.At page press "Account details" 4.In Combobox/components "Password change" 5.User input current password in "Current password" 6.User input new password in "New password" 7.User input re-enter new password in "Confrim new password" 8.User Click "Save change" | Display show:"Account details changed successfully.". |  |  | 25-Nov-2025 | Đạt |  | Pass | Đạt
MA_11 | Verify that user can't set new password identical to current password |  | 1.User launch website Agest 2.User Login 3.At page press "Account details" 4.In Combobox/components "Password change" 5.User input current password in "Current password" 6.User input current password in "New password" 7.User input current password in "Confrim new password" 8.User Click "Save change" | Display show error. |  |  | 25-Nov-2025 | Đạt |  | Fail | Đạt |  |  |  |  | Bug 26

## Bug List
Bug List |  |  |  | New | 11 |  | Fixed | 0 |  | Closed | 0
|  |  |  | Assigned | 0 |  | In Verification | 0 |  | Rejected | 0
|  |  |  | In Progress | 0 |  | Re-opened | 0
ID | Summary | Description | Pre-Condition | Steps to Reproduce (Including Expected Behaviour and Observed Behaviour) | Build found | Date found | Platform | Reproducibility | Severity | Frequency | Priority | Keyword | Reported by | Reviewed by | Status | Resolution | Build fixed | 2.0 Regressed by | 3.0 Regressed by | Note
Bug 01 | The number of reviews is different from the number of customers who review a product. | This bug happens with all products. |  | Steps: 1. Go to AGEST website 2. Open any product 3. View the number of reviews 4. View the number of customer reviews 4. Compare the numbers Expected result: The number of reviews is consistent. Observed result: The number of reviews is inconsistent. | 1.0 | 25-Nov-2025 | Version 140.0.7339.81 | Always | Minor | Always |  | Reviews | Thoa |  | New | n/a
Bug 02 | Error message displays when user clicks on "Update Cart" button aftter changing quantity of product in Cart page. |  |  | Steps: 1. Launch the AGEST website 2. Go to the cart page 3. Update quantity 4. Click “Update Cart” button Expected Result: Cart should update normally. Actual Result: Error message "Sorry, we are currently experiencing technical difficulties with our cart system. Please try again later." appears. | 1.0 | 25-Nov-2025 | Version 140.0.7339.81 | Always | Minor | Always |  | Shopping | Thoa |  | New | n/a
Bug 03 | The system displays the message: "Quantity of product × "Product name" has been added to the cart. View cart <br> <li></div>" when the user adds a very large quantity to the cart. For example: "9223372036854775807 × "Floral Elegance Sun Hat" has been added to the cart. View cart <br> <li></div>" | When adding very large quantities, the system displays a message with broken HTML. |  | 1. Add extremely large quantity of a product. 2. Observe the cart message. Expected Result: Message should display correctly with valid HTML. Actual Result: Message shows broken HTML tags. | 1.0 | 25-Nov-2025 | Version 140.0.7339.81 | Always | Minor | Always |  | Product | Thoa |  | New | n/a
Bug 04 | The page-switching button in the website’s menubar is not located on the header. |  |  | Steps: 1. Go to AGEST website on phone 2. Scroll to the bottom of the webpage Expected result: Menubar located on header or in menu icon Observed result: Menubar in footer. | 1.0 | 25-Nov-2025 | Mobie, Redmi note 11(android 13) | Always | Minor | Always |  | Menubar,UI | Đạt |  | New | n/a
Bug 05 | The website takes more than 4 seconds to load on the first visit. |  |  | Steps: 1. Go to AGEST website on phone/desktop Expected result: Loading less 4 seconds Observed result: Loading more 4 seconds | 1.0 | 25-Nov-2025 | -Mobie, Redmi note 11(android 13) -Emutilation android 16 -Desktop Chrome(142.0.7444.176) x64 | Always | Minor | Always |  | Performance, Loading | Đạt |  | New | n/a
Bug 06 | Cannot see password when creating account in "checkout" page. |  |  | Steps: 1. Go to AGEST website 2. Add any product to "Cart" 3. At page "Shopping Cart" 4. Click "Proceed to checkout" 5. Scroll down and click on checkbox "Create an account?" 6. Input Password 7. Click icon "eyes" Expected result: Show hidden password. Observed result: Hidden password not visible | 1.0 | 25-Nov-2025 | -Desktop Chrome(142.0.7444.176) x64 | Always | Minor | Sometimes |  | Icon"eyes", password | Đạt |  | New | n/a
Bug 07 | Item "Sophisticated Striped Midi Dress" error wrong product link on page Home |  |  | Steps: 1. Go to AGEST website 2. At "Home" page 3. Srcoll down and click "Sophisticated Striped Midi Dress" item Expected result: Show detail card "Sophisticated Striped Midi Dress" Observed result: Show detail card "Midnight Bloom Crochet Dress" | 1.0 | 25-Nov-2026 | -Desktop Chrome(142.0.7444.176) x65 | Always | Minor | Always |  | details card, item,product | Đạt |  | New | n/a
Bug 08 | Product link not working |  |  | Steps: 1. Go to AGEST website 2. At "Home" page 3. Srcoll down and click "Sunset Glow Utility Dress" item Expected result: Show detail card "Sunset Glow Utility Dress" Observed result: Not show detail item "Sunset Glow Utility Dress" | 1.0 | 25-Nov-2027 | -Desktop Chrome(142.0.7444.176) x66 | Always | Minor | Always |  | details card, item,product | Đạt |  | New | n/a
Bug 09 | The search icon is not on the menu bar when the user opens the web on the mobile. |  |  | Steps: 1. Laurch AGEST website on mobile 2. Go to "Home" page Expected result: The search icon on the menu bar. Observed result: The search icon is not on the menu bar. | 1.0 | 25-Nov-2025 | Mobile, PC | Always | Minor | Always |  | Search | Phong |  | New
Bug 10 | When the user has removed the product from the cart, the system displays incorrect UI on mobile. |  | There is one item in the cart | Steps: 1. Laurch AGEST website on mobile 2. Go to "Cart" page 3. Click on detele product icon Expected result: The check mark icon is located on the left side of the line of text that the product was deleted from. Observed result: The check mark icon is located on the left above the "Undo?" box. | 1.0 | 25-Nov-2025 | Mobile, PC | Always | Minor | Always |  | Cart | Phong |  | New
Bug 11 | When the user opens the app on mobile, the icon to open the menu panel is in the wrong position. |  |  | Steps: 1. Laurch AGEST website on mobile 2. Go to "Home" page Expected result: The icon to open the menu panel is located on the left side of the menu bar, on the right is the website name icon. Observed result: The icon to open the menu panel is located on the right side of the menu bar, on the right is the shopping cart icon. | 1.0 | 25-Nov-2025 | Mobile, PC | Always | Minor | Always |  | Home | Phong |  | New
Bug 12 | The password less twelve characters long. To make it stronger, use upper and lower case letters, numbers, and symbols like ! " ? $ % ^ & ) |  |  | Steps: 1.Open page "MY ACCOUNT" for Agest 2.User select password textbox 3.User input password 4.User input less 12 character, contain 1 special character, upper and lower case (14Zxc!7369) Expected result: Observed result: | 1.0 | 25-Nov-2026 | -Desktop Chrome(142.0.7444.176) x66
Bug 13
Bug 14
Bug 15
Bug 16
Bug 17
Bug 18
Bug 19
Bug 20
Bug 21
Bug 22
Bug 23
Bug 24
Bug 25
Bug 26
Bug 27

## Trang tính8
Build | Feature | Bug Resolution | Severity | Frequency | Priority | TC Status | Bug Status | TC Result | Platform
1.0 | Register | n/a | Critical | Everytime | Urgent | Open | New | Passed | Windows
2.0 | Login | Fixed | Major | Sometimes | High | Closed | Assigned | Failed | Mac
3.0 | My Account | Not Reproducible | Minor | Hardly | Medium |  | In Progress | Blocked | Mobile
| Home & About | Not a Bug | Trivial |  | Low |  | Fixed | Skipped
| Shop & Products | Duplicated |  |  |  |  | In Verification
| Cart & Order | Won’t Fix |  |  |  |  | Closed
| Blog | Deferred |  |  |  |  | Re-opened
| Other | Feature Limitation |  |  |  |  | Rejected